Discussion points for 18Nov25 meeting

Overall summary

I’m moving to a new position very soon (beginning Feb; less than 3 months with holidays in between). Joe is aware that some work and obligations will be moving with me, and I personally want to complete the things that I’ve started. I will have at minimum 5 hours/wk to devote to these things, with potential for more time as allowed by new position obligations and workload. Grants are another story that can get real complicated – cross those bridges when we get there.

Ongoing projects and status

- PPP – compiling all the code and data, cleaning everything up and finalizing figures. I have a paper skeleton that I’m going to try to have fully fleshed out by the holidays, and submitted before leaving?

  - Goal – submit paper before transition

    - Figure drafts for whole paper – end of next week 11/28

    - Paper draft by end December

    - Potential submission by end January

- PILA management legacies – this is honestly still just a good idea based on preliminary analyses. What are the pathways by which management conveys general forest resilience, beyond just fuels reductions?

  - Goal – preliminary analyses and skeleton that can be further developed or handed off

    - Feasibility assessment; plot support, what’s confounded, etc

      - Does disturbance happen? What are the consequences

      - What are the bounds of this problem?

- PILA dendrochronology – I’m interested in staying involved here to the degree possible

  - Goal – continue collaboration

Logistical/admin things to figure out

Basically, it’s all transitionary stuff – how do we do this cleanly? We need to make a plan.

- FIA plot locations  my basic expectation is that when I move over to TNC, I lose access to FIA plot locations. Is this correct? As far as USFS is concerned, my position will be functionally exactly the same (i.e., non-employee official affiliate), so can all this stuff transfer over with me to facilitate finishing up these projects?

- Computer equipment  RMRS is supposed to supply stuff for this position. Do we need to return PNW supplies and reissue from RMRS, or can stuff transfer over with me?

- USDA/USFS profiles, etc… basically the same questions, does this all migrate with me or do we start over from scratch? LinkPass, etc?

- Corvallis trip –

  - Options are second week or so of December; or second/third week of January